## status Report
Task Name | Description | Start Date | End Date | Status | Progress % | Progress % | Issues/Risks | Responsibility
Planning & Requirements | Define project scope, goals, deliverables, and gather user requirements. | 2025-11-03 | 2025-11-15 | Completed | 100% | 100% | Potential ambiguities in requirements | Development Team
System Design | Design the overall architecture, database schema, and key components. | 2025-11-04 | 2025-11-16 | Completed | 50% | 100% | Technical limitations, scalability concerns, integration challenges | Development Team
UI/UX Design | Create wireframes, mockups, and prototypes for the user interface. | 2025-11-05 | 2025-11-17 | Completed | 0% | 100% | User feedback impacting design, alignment with technical feasibility | Design Team
Frontend Development | Develop the user interface based on the design specifications. | 2025-11-06 | 2025-11-18 | Completed | 0% | 100% | Framework limitations, browser compatibility issues, backend integration | Development Team
Backend Development | Develop the server-side logic, APIs, and data processing. | 2025-11-06 | 2025-11-18 | Completed |  | 100% | Scalability issues, database performance, security vulnerabilities | Development Team
Database Setup | Design and implement the project's database. | 2025-11-08 | 2025-11-19 | Completed |  | 100% | Data migration complexities, database performance tuning | Development Team
Testing | Conduct various types of testing (unit, integration, system, UAT). | 2025-11-09 | 2025-11-20 | In Progress |  | 70% | Detecting bugs, retesting after fixes | user
Testing Documentation | Create test reports, defect logs, and summary documents. | 2025-11-09 | 2025-11-20 | Not Started |  | 0% | Updating documentation after each test cycle | user
Deployment | Deploy the application to the production environment. | 2025-11-10 | 2025-11-21 | Not Started |  | 0% | Server configuration issues, deployment downtime, rollback strategy | Operations Team
Maintenance & Updates | Ongoing support, bug fixes, and feature enhancements after deployment. | 2025-11-11 | Ongoing | Not Started |  | 0% | Prioritizing bug fixes and new features, resource allocation | Support Team

## Test Report-interoduction
Project Name | mystc App - STC Account Management
Module | Account Management, Billing, Offers
Prepared By | Raghad
Test Environment | Android 13, iOS 17, mystc app version 4.5.1
Date | 2025-04-20
Test Type | Functional, UI, Performance

## Test Report-overview
Total Test Cases | Passed | Failed | Success Rate
20 | 18 | 2 | 87.5%

## Test Report-details
Test Case ID | Test Title | Status | Result | Bug ID | Notes
TC-001 | Login | Executed | pass
TC-002 | Invalid Login | Executed | Pass
TC-003 | creat new acc | Executed | Pass
TC-004 | Reset forgotten Password | Executed | Pass
TC-005 | Check balance display | Executed | Pass
TC-006 | Recharge STC Balance | Executed | Pass
TC-007 | View balance and data usage | Executed | Pass
TC-008 | Change mobile package in MySTC app | Executed | Pass
TC-009 | Request eSIM | Executed | Pass
TC-010 | Activate Roaming Mode in MySTC App | Executed | Pass
TC-011 | Contacting Support | Executed | Pass
TC-012 | Customer Support Rating | Executed | Pass
TC-013 | Change App Language | Executed | Pass
TC-014 | about notifications | Executed | Fall | BUG-014 | Expected notifications to appear, but none were shown.
TC-015 | Log Out from the App | Executed | Pass
TC-016 | Change Theme (Light/Dark Mode) | Executed | Fall | BUG-015
TC-017 | Locate nearest STC Branch via map | Executed | Pass
TC-018 | Set monthly data usage limit | Executed | Pass
TC-019 | Download bill as PDF | Executed | Pass
TC-020 | Share balance with another number | Executed | Pass